## Table 1
B.1 2020- 2029 Capital Improvements Program
2020 | Project |  | Estimated Cost ($1,000) | Possible Funding Sources |  |  | Status Update
Public Restroom Upgrade |  |  | 19 | GF Funded DOLA/GF GF GF GF GF Funded by Fishing is Fun/GF GF GF GF GF Funded by CDBG GF match DOLA/GF GF Funded-PPRTA “A” List Funded by private donation TC PD (For pool & Sallie Bush) GF |  |  | Potential Funding through Stimulus
Repair Maple Street Bridge |  |  | 35 |  |  |  | COMPLETED - DOLA/GMF Funded - Flood Recovery Project 2020
Lake Improve Water Quality (clear up muddy water) |  |  | -- |  |  |  | Work Funded to be completed with Lake Wall & Drain Repair
Lake Divert SW from Hotel Street to Fountain Creek |  |  | 13 |  |  |  | PPRTA Ballot November 2022
Lake Divert SW from Ute Pass Avenue to Creek |  |  | 8 |  |  |  | PPRTA Ballot November 2022
Lake Divert SW from Foster Avenue to Fountain Creek |  |  | 5 |  |  |  | PPRTA Ballot November 2022
Lake Sediment Dredging (after SW diversions) |  |  | 23 |  |  |  | PPRTA Ballot November 2022
Lake Inlet Valves Automated Controls |  |  | 12 |  |  |  | COMPLETED - Funded by Colorado Parks & Wildlife Fishing Is Fun Grant
Town Hall Monumental Sign |  |  | 8 |  |  |  | Collaborating with Fire Department on Combined Sign In Progress
Town Hall Increase Parking and Pave |  |  | 9 |  |  |  | COMPLETED - GMF General Fund
Lake ADA Fishing Pier |  |  | 10 |  |  |  | El Paso County Community Development Block Grant - Application Processing In Progress
El Paso Trail Road Drainage Improvements |  |  | 41 |  |  |  | PPRTA Ballot November 2022
Iona Avenue Drainage/Road Repairs |  |  | 32 |  |  |  | PPRTA Ballot November 2022
Stilling Basins (roadway drainage improvements) |  |  | 66 |  |  |  | Work Funded by PPRTA - Project in Progress
Replace Altitude Sign at Hotel Street |  |  | 3
Construct Trail Red Devil Mountain |  |  | 7 |  |  |  | COMPLETED - Red Devil Mountain Annexation 2020
Increase Parking Capacity Along Pool Park Fence |  |  | 5 |  |  |  | Work Scheduled In Progress
Replace Steel Culverts Town-wide (Phase 1) |  |  | 10 |  |  |  | Need a Comprehensive Roads Plan - Grant Application Submitted to DOLA Sept 3, 2021
2021 | Project |  | Estimated Cost ($1,000) | Possible Funding Sources |  |  | Status Update
Flood Control North end of Oak Street |  |  | 425 | FCWFCD Project #24 |  |  | FCWFCD funding is 50/50 match
Flood Control Armor Creek at GMF Road Bridge |  |  | 100 | FCWFCD Project #23 |  |  | FCWFCD funding is 50/50 match
Flood Control Bank Stabilization in Gazebo Park |  |  | 150 | FCWFCD |  |  | FCWFCD funding is 50/50 match
Flood Control Replace El Paso Avenue East Crossing |  |  | 60 | FCWFCD Project #24 |  |  | FCWFCD funding is 50/50 match
Lake Reconfigure Outlet and Overflow |  |  | 50 | GOCO |  |  | El Paso County Community Development Block Grant - Application Processing In Progress
Lake Replace Walls at East and South ends |  |  | 40 |  |  |  | El Paso County Community Development Block Grant - Application Processing In Progress
Lake Armor West Shore New Path Installation |  |  | 5 | TC Volunteers |  |  | El Paso County Community Development Block Grant - Application Processing In Progress
Gazebo Park Ground Cover West and South Banks |  |  | 10
Gazebo Park Island Landscaping |  |  | 10
Pool Park Irrigation System |  |  | 20 | GOCO |  |  | Backflow Preventor Installation In Progress
Pool Park Restrooms |  |  | 60 | COGO/PD
Community Events Information Board |  |  | 9 | Chamber and Donations |  |  | Wayfinding Signage Project In Progress - funded by Kirkpatrick Foundation Grant
Replace Bridge Oak Street |  |  | 30 |  |  |  | PPRTA Ballot Novebmer 2022
Plant Trees Arbor Day |  |  | 5 | PD
Replace Steel Culverts Town-wide (Phase 2) |  |  | 10 |  |  |  | Need a Comprehensive Roads Plan - Grant Application Submitted to DOLA Sept 3, 2021
Renovate Old Marshal’s Office |  |  | 30 | GF/PD |  |  | Potential History Colorado Grant Funding - Need a Historical Preservation Board to Champion
102
2022 | Project | Estimated Cost ($1,000) |  | Possible Funding Sources |  |  | Status Update
Flood Control Detention Pond on Crystal Creek |  | 350 |  | FCWFCD Project #25 Flood |  |  | FCWFCD funding is 50/50 match
Flood Control Replace Bridge at Hotel Street |  | 506 |  | FCWFCD Project #26 Flood |  |  | FCWFCD funding is 50/50 match
Flood Control Bank Stabilization Behind Motel |  | 100 |  | FCWFCD Project #27 Flood |  |  | FCWFCD funding is 50/50 match
Upgrade Park Playground |  | 15 |  | GOCO Grant/PD |  |  | Next Step Parks, Rec, & Trails Advisory Board Community Outreach - Prep for Grant Application Submittal
Streetscaping Ute Pass Avenue with Traffic Calming |  | 250 |  | SAFET
Historic Interpretive Panels |  | 25 |  | UPHS/PD
Plant Trees on Arbor Day |  | 5 |  | PD
Construct Trail at Livengood Gulch |  | 8 |  | TC |  |  | Parks, Recreation, & Trails Advisory Board
Construct Spur Trail to Empire Power Plant site |  | 5 |  | TC |  |  | Parks, Recreation, & Trails Advisory Board
2023 | Project | Estimated Cost ($1,000) |  | Possible Funding Sources |  |  | Status Update
Renovate Swim Pool Ute Pass Avenue Overlay Construct Trail at Mt. Rebecca |  | $80 $300 $15 |  | GOCO PPRTA-Priority “B” List FOTP/TC/MHYC |  |  | Next Step Parks, Rec, & Trails Advisory Board Community Outreach - Prep for Grant Application Submittal PPRTA Ballot November 2022
2024 | Project | Estimated Cost ($1,000) |  | Possible Funding Sources |  |  | Status Update
Bridge Rehabilitation/Replacement (several) Replace Bridge Ute Pass Avenue at Crystal Creek |  | $123 $300 |  | PPRTA-Priority “B” List PPRTA/CDOT |  |  | PPRTA Ballot November 2022
2025 | Project | Estimated Cost ($1,000) |  |  | Possible Funding Sources |  | Status Update
Gazebo Park-Island Bridge Replacement |  | 8 |  | GF
2026 | Project | Estimated cost ($1,000) |  |  | Possible Funding Sources |  | Status Update
Construct Trail Kirkpatrick to Mt. Esther |  | 12 |  | TC |  |  | Parks, Recreation, & Trails Advisory Board
103
2027 | Project |  | Estimated cost ($1,000) |  |  | Possible Funding Sources | Status Update
Construct Trail- Crystal Trail to Crystal Reservoir |  |  | 10 | TC/FOTP |  |  | Parks, Recreation, & Trails Advisory Board
2028 | Project |  | Estimated cost ($1,000) |  |  | Possible Funding Sources | Status Update
Restore Crystal Falls at Hydro Plant (flume) |  |  | 30 | UPHS/PD |  |  | Parks, Recreation, & Trails Advisory Board
2029 | Project |  | Estimated cost ($1,000) |  |  | Possible Funding Sources | Status Update
Gazebo Park-Pavilion/ Stage |  |  | 70 | GOCO/PD |  |  | Parks, Recreation, & Trails Advisory Board - Potential GOCO/CDBG Grant Opportunities
* KEY TO FUNDING SOURCES CSU Colorado Springs Utilities CDBG HUD Community Development Block Grants DOW State Dept of Wildlife DOLA State Dept of Local Affairs FIF Fishing is Fun (DOW) GF GMF General Fund TF GMF Trails Funds GOCO Great Outdoors Colorado Trust Fund HGMFF Historic GMF Foundation PD Private Donations PPCF Pikes Peak Community Foundation PPRTA Pikes Peak Rural Transportation Authority FCWFCD Fountain Creek Watershed Flood Control District ST State Trails Fund SAFET Transportation Enhancement Funds UPHS Ute Pass Historical Society
104